## Sheet1
DRAFT TFM TImeline
FY 2025 TFM 2-4700 Timeline* | TFM Team Assignment | Review Assignment | Date | Comments
DRAFT #1
Internal Stakeholder Review (March -June)
Send out prior year version for review & comments to FRAD and GFAB |  |  | 2024-03-14
Set up meetings with entities to discuss guidance changes
Set up meetings with GAO to discuss guidance changes
Provide a monthly status to CRT members.
Internal Stakeholder comments due date |  |  | 2024-06-24
FR Staff Management Review - Draft #1 comments. | TFM Team | TFM Team | 6/27 to 7/8 | Any commets from this Mangement Review are to be addressed prior to submission of the draft to the stakeholders.
| Denise | Marsha
Update Authority (4702)
Update Definition of Terms (4703)
Update FR Processing Key Dates
Update Closing Package Requirements (4705-4705.70)
Update Year-End Intragov. Reconciliation Process (4705.75)
Update CFO Procedures for Intragov. Activity/Balances ( 4705.80)
Update Intragov. Activity/Balances Reconciliation ( 4706.10)
Federal Intragov. Transaction APG ( 4706.15)
Intragov. Fiduciary Confirmation System ( 4706.20)
Non-Fiduciary Transactions (4706.25)
Qtrly Intragov. Reconciliation ( 4706.30)
All Dates Chart (p. 6)
Collection of ATB Data ( 4707.10)
FACTS I System Access ( 4707.15)
FACTS I Reportable Data ( 4707.20)
MAF ( 4707.20aa)
ATB ( 4707.20b)
Special Accounts ( 4707.20c)
Treasury Managed Trust Fund Accounts ( 4707.20d)
Parent/Child Reporting ( 4707.20e)
ATB Reports Transmission Methods ( 4707.20f)
Proprietary Balances in Canceled Accounts ( 4707.20g)
| Phillip | Denise
DRAFT #2
Stakeholders Review
Send out Draft #2 for comment to the following:
Update Scope and Applicability (4701) |  |  | 2024-07-09
Update Authority (4702)
Update Definition of Terms (4703)
Update FR Processing Key Dates
Update Closing Package Requirements (4705-4705.70)
Update Year-End Intragov. Reconciliation Process (4705.75)
Update CFO Procedures for Intragov. Activity/Balances ( 4705.80)
Update Intragov. Activity/Balances Reconciliation ( 4706.10)
Federal Intragov. Transaction APG ( 4706.15)
Intragov. Fiduciary Confirmation System ( 4706.20)
Non-Fiduciary Transactions (4706.25)
Qtrly Intragov. Reconciliation ( 4706.30)
All Dates Chart (p. 22)
Collection of ATB Data ( 4707.10)
FACTS I System Access ( 4707.15)
FACTS I Reportable Data ( 4707.20)
MAF ( 4707.20aa)
ATB ( 4707.20b)
Special Accounts ( 4707.20c)
Treasury Managed Trust Fund Accounts ( 4707.20d)
Parent/Child Reporting ( 4707.20e)
ATB Reports Transmission Methods ( 4707.20f)
Proprietary Balances in Canceled Accounts ( 4707.20g)
Appendix 1 (Reclassified Financial Statements and Line Descriptions)
Appendix 2 ( Sample Agency A Reclassification Entry Summary)
Appendix 3 ( FR Notes Instructions)
Appendix 4 (Other Data Format)
Appendix 4 (Other Data Instructions)
Appendix 5 Department Codes
Appendix 6 RC Crosswalk to Financial Statements
Appendix 7 Federal Intragov. Transactions Categories of SGL Accounts
Appendix 8 FY 11 CFO Representation
Appendix 9 BSF Codes
OFAS & OMB copies of TFM for review (via email)
Audit community (via email). Kelly McFadden is the POC & she will distribute the documents to the audit community.
Federal entities (Connect.gov) |  |  |  | Set up CRT meeting to discuss changes for FY25
Stakeholders comments due date (COB) |  |  | 2024-07-23
TFM POCs incorporated any applicable changes into their assigned appendices. |  |  | 7/23 to 7/26
FR Staff Management Review - Draft #2 comments. |  |  | 7/29 to 8/2
DRAFT #3
GAO Review
Send out Draft #3 to GAO (via email) |  |  | 2024-08-05
GAO comments due date |  |  | 2024-08-23
TFM POCs incorporated any applicable changes into their assigned appendices. |  |  | 8/26 to 8/30
Management Review - Draft #3 GAO comments |  |  | 9/3 to 9/10 | Signatures required from FRAD Management for Final Draft.
Final Draft | TFM Team | TFM Team
Master copy given to TFM Editors & OCC | TFM Team | TFM Team | 2024-09-12
TFM Coordinator provides Final TFM for website | TFM Team | TFM Team
Receive and coordinate any additional comments and Editors changes
Execute final review before publication | TFM Team | TFM Team
TFM workflow is approved by all parties |  |  | 2024-10-01
TFM Editors post to the website |  |  | 2024-11-05 | Send CRT and GTAS email blast announcing publication.
Authorize the GTAS system administrators to send users a global notification that the 2025 TFM is published.
Verify the TFM publication to the source document. Communicate any applicable changes to TFM Editors.
*Dates subject to change
Points of Contact
Main Chapter - Teri Magers
Appendix 1a & 1b - Justin Sheline/Jason Chichester
*Appendix 2 - 10 - Wes Vincent/Terrence Francisco
Appendix 11 - Lisa Midcap
Appendix 12 - Rebekah Wingrove

## Sheet2
Attachment A
Points of Contact
Main Chapter - Teri Magers
Appendix 1 - Teri Magers
Appendix 2 - Luke Sheppard
Appendix 3 - Mallorie Davis
Appendix 4 - Mallorie Davis
Appendix 5 - Jason Chichester
Appendix 6 - Vivian Fitzgerald
Appendix 7 - Vivian Fitzgerald
Appendix 8 - Lisa Midcap
Appendix 9 - James Full, Jacki Parsons
Appendix 10 - Lisa Midcap